## Notice
Insérer le logo du projet ou le logo de l’organisme | Référence du projet : 202x-1-FR01-KA210-…...-…………….. Programme Erasmus+ action clé 2 Partenariat simplifié
Ce document est un modèle de fichier de suivi budgétaire que le coordinateur peut utiliser avec ses partenaires, afin de suivre la consommation budgétaire de la subvention
Il s’agit d’un exemple
Les bénéficiaires sont libres de l’adapter
Ce tableau est composé de plusieurs feuilles,
chaque feuille correspond à un organisme partenaire.
La dernière feuille montre la consommation totale du budget par partenaire et par module de travail.
DERNIERE MISE À JOUR DU TABLEAU : JJ/MM/AA

## USSAP
COORDINATOR ORGANISATION(USSAP - OID E10286993)
ACTIVITIES | STEP | SCHEDULED DATES | DATES ACHIEVED | PROVISIONAL BUDGET | BUDGET DEPENSÉ
WP1 : Project management | En cours | M1 – M24 |  | 6000
WP2 : Communication and dissemination | En cours | M3 – M24 |  | 4000
WP3 : Field surveys | En cours | M3 – M8 |  | 1500
WP4 : Training programme for the MOOC | En cours | M4 – M21 |  | 3500
WP5 : Online learning platform for the MOOC | Non commencé | M7 – M24 |  | 4500
|  |  | TOTAL | 19500 | 0

## AUX COULEURS DU DEBA
PARTNER ORGANISATION (AUX COULEURS DU DEBA - OID E10091330)
ACTIVITIES | STEP | SCHEDULED DATES | DATES ACHIEVED | PROVISIONAL BUDGET | BUDGET DEPENSÉ
WP1 : Project management | En cours | M1 – M24 |  | 4000
WP2 : Communication and dissemination | En cours | M3 – M24 |  | 3000
WP3 : Field surveys | En cours | M3 – M8 |  | 1500
WP4 : Training programme for the MOOC | En cours | M4 – M21 |  | 5000
WP5 : Online learning platform for the MOOC | Non commencé | M7 – M24 |  | 9000
|  |  | TOTAL | 22500 | 0

## STANDO LTD
PARTNER ORGANISATION (STANDO LTD - OID E10168250)
ACTIVITIES | STEP | SCHEDULED DATES | DATES ACHIEVED | PROVISIONAL BUDGET | BUDGET ACHIEVED
WP1 : Project management | En cours | M1 – M24 |  | 4000
WP2 : Communication and dissemination | En cours | M3 – M24 |  | 3000
WP3 : Field surveys | En cours | M3 – M8 |  | 3000
WP4 : Training programme for the MOOC | En cours | M4 – M21 |  | 3500
WP5 : Online learning platform for the MOOC | Non commencé | M7 – M24 |  | 4500
|  |  | TOTAL | 18000 | 0

## SUIVI BUDGET
BUDGET SUMMARY
ORGANIZATION | WP1 Project management |  | WP2 Communication and dissemination |  | WP3 Field surveys |  | WP4 Training programme for the MOOC |  | WP5 Online learning platform for the MOOC |  | TOTAL PROJECT
| PROVISIONAL BUDGET | BUDGET ACHIEVED | PROVISIONAL BUDGET | BUDGET ACHIEVED | PROVISIONAL BUDGET | BUDGET ACHIEVED | PROVISIONAL BUDGET | BUDGET ACHIEVED | PROVISIONAL BUDGET | BUDGET ACHIEVED | PROVISIONAL BUDGET | BUDGET ACHIEVED
USSAP | [10 empty] | 19500 | 0
AUX COULEURS DU DEBA | [10 empty] | 22500 | 0
STANDO LTD | [10 empty] | 18000 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0
| 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0%

## Feuil1 (hidden)
En cours
Non commencé
Finalisé